## 4. Achieve excellent outcomes
Excellent Outcomes |  |  | Ormiston Latimer Academy
Vision | [9 empty] | Key Performance Indicators
|  |  |  | 2024 |  |  |  |  | 2025 | [7 empty] | .RAG
| Objective (why?) | Lead (who?) | Actions (how?) | July | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Monitoring and quality assurance | HT1 | HT2 | HT3 | HT4 | HT5 | HT6 | Resource or budget implications | Estimated cost | Still in scope? Y/N
2 | Develop each pupils entrepreneurial and employability skills through the curriculum and personal development opportunities, so that pupils are prepared for the next steps of their educational journey and the wider world. | DB/GM | Recruit a 'Post-16 and CIAEG Lead'
Align our curriculum offer with the Gatsby benchmarks
Organise work experince opportunities
Plan and deliver a Workskills qualifiication developing the employability skills our pupils need to be successful beyond school
Develop relationships with local, regional and national businesses to provide opportunities for our pupils to engage in the world of work
3 | Develop and embed robust systems which suppoort the transition of pupils onto the next steps of their educational journey, reducing the numbers of pupils who become NEET over the 3 years after leaving the academy. | DB/GM | Work with pupils to ensure that post-16 applications are made in a timely manner
Liaise with post-16 education providers to create opportunities for all pupils who attend OLA.
Provide guidance to both staff and pupils regarding any developments in the post-16 education landscape
Develop and maintain accurate post-16 application data and regularly evaluate
Work with the local authority to mitigate the risk of pupils becoming NEET
Key
| Explore | E
| Prepare | P
| Deliver | D
| Sustain | S
How will you measure the impact of your actions?
- 100% EET at post 16
What is your long term vision for this priority?
At Ormiston Latimer Academy, our vision is to ensure that all pupils including those with SEND are supported to achieve the best possible academic outcomes and are ready for the next steps of the educational journey.

## 3 Year Planner
| Achieve excellent outcomes |  |  |  |  | Ormiston Latimer Academy
|  |  | Rationale Why does it need to improve? |  |  |  | 2024/25 | [11 empty] | 2025/26 | [10 empty] | 2026/27
| Project / improvement strand | Linked Trust priority |  | Where do you want to be in 3 years' time? | Key documents/policies | Budget implications | July | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Sept | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | June | July | Key
1 | Pupils holistic developments | Improve behaviour and culture | Pupils behaviour in 2023/24 was extremely challenging with a significant number of Fixed Team Suspensions (FTS) across the academic year. There was very little to no reintegration back into mainstream education because pupils were not equipped with the skills and qualities that they needed to be successful. | Over the next 3 years we want to achieve the following key objectives; a plateuing of FTS when compared year on year, an increase in pupils returning to mainstream education, pupils feeling more positive about their futures as evidenced through fully embedded assessment tools (To be explored). | PASS - GL Assessment (gl-assessment.co.uk) | Subscription/purchase of suitable assessment tools.
2 | Vocabulary and comprehension | Strengthen reading | Historically there has been minimal focus on reading devlopments within the acdemy at a whole school level. | Over the next 3 years we want to achieve the following key objectives; a focus on vocabulary and comprehension is clearly defined and embedded in each lesson, an increase in the % of pupils make progress in their reading ability (Actual Reading Age vs Chronological Reading Age), a staff team that is trained and confident in developing lieracy skills in their respective subject. |  | Staff training costs, subscription/purchase of reading platforms and assessment tools
3 | Teaching and learning approaches | Develop great teaching | There are currently inconsistencies in terms of the quality and approach of teaching and learning across the academy. | Over the next 3 years we want to achieve the following key objectives; There are clearly defined, evidenced based approaches to teaching and learning across all areas of the school (EEF 5 a day), all lessons are good or better across all areas of the school, staff have a sound understanding of SEND and this is evident in their practices in every lesson. | EEF blog: ‘Five-a-day’ to improve SEND outcomes ¦ EEF (educationendowmentfoundation.org.uk)
4 | Reduce NEET data | Achieve excellent outcomes | The % of pupils 'at risk' of becoming NEET was not clearly defined as a result of ineffective tracking, monitiring and leadership of post-16 applications. | Over the next 3 years we want to achieve the following key objectives: Establish effective relationships with both local, regional and national training providers so that pupils are provided with the best posible opportunities for the future, CIAEG and post-16 focus is embedded through the curriculum, there is a decline in the number of pupils 'at risk' of becoming NEET. |  | Recruitment of a permanent 'Post-16 and CAIEG Lead', Budget for visits to training providers and any associated costs.
5 | Develop stakeholder relationships and support | Improve behaviour and culture | Relationships have been established with stakeholders including the LA, and there is a willingness to work with Latimer Academy however, this support has not always been utilised effectively. | Over the next 3 years we want to achieve the following key objectives; A fully embedded specialist taskforce approach as per the DfE's APST guidance, personalised timetables for pupils who need support outside of the classroom encompassing a multi-agency offer and approach, Latimer academy to be a identified as a beacon of how AP amd multi-agency work together to promote the educational successes of all pupils. | Alternative provision specialist taskforces (APST) - GOV.UK (www.gov.uk) | Recruitment of an Attendance officer.